## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME:
INTERN NAME:
DOCUMENT NAME: | TEST PLAN
CREATED ON: | DD-MMM-YYYY
Purpose of Document
A Test Plan is a detailed document that describes the test strategy, objectives, schedule, estimation, deliverables, and resources required to perform testing for a software product.
Test Plan helps us determine the effort needed to validate the quality of the application under test.
The test plan serves as a blueprint to conduct software testing activities as a defined process, which is minutely monitored and controlled by the test manager
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments are added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled

## TEST PLAN
TEST PLAN
PROJECT NAME | CollegeHub
PROJECT ID
INTERN NAME | Prajakta Pattanaik
PROJECT MANAGER | Harshada Topale
INTRODUCTION
(Brief introduction of the test strategies, process, workflow and methodologies used for the project)
The development of CollegeHub followed an iterative and modular approach, with features being implemented and tested incrementally throughout the development lifecycle. The project workflow included requirement analysis, interface design, backend and database development, integration, and system validation. Various testing strategies such as unit testing, integration testing, functional testing, user interface testing, and database testing were employed to ensure the reliability, accuracy, and performance of the application. Continuous debugging and validation were carried out to identify and resolve errors, resulting in a robust and user-friendly web platform.
SCOPE
IN SCOPE (Defines the features, functional or non-functional requirements of the software that will be tested)
The scope of testing for CollegeHub includes both functional and non-functional requirements of the system. Functional requirements covered under testing include user registration and authentication, college browsing, course-based filtering, pagination, API communication, and database operations for storing and retrieving college information. Non-functional requirements include system performance, reliability, responsiveness, usability, security, and compatibility across different browsers and operating systems to ensure a seamless user experience.
OUT SCOPE (Defines the features, functional or non-functional requirements of the software that will NOT be tested)
The scope of testing for CollegeHub does not include third-party services, server deployment environments, stress and load testing under large-scale traffic conditions, or security testing against advanced cyber threats. Features planned for future enhancements, such as AI-based recommendations, college comparison tools, and mobile application support, are also excluded from the current testing scope.
QUALITY OBJECTIVE
(Mention the overall objective that you plan to achieve without your testing)
The primary objective of testing CollegeHub is to ensure that the application conforms to its functional and non-functional requirements and meets the expected quality standards. The testing process aims to verify the correctness, reliability, performance, and usability of the system, while identifying and resolving defects before deployment. This ensures that users can seamlessly browse and access college information through a secure, efficient, and user-friendly platform.
ROLES AND RESPONSIBILITIES
(Detail description of the Roles and responsibilities of different team members)
As CollegeHub was developed by a single team member, all responsibilities related to requirement analysis, user interface design, frontend development, backend development, database management, API integration, testing, debugging, and documentation were handled by the developer. The developer was responsible for designing the system architecture, implementing the application using HTML, CSS, JavaScript, Node.js, Express.js, and PostgreSQL, conducting functional and integration testing, identifying and resolving defects, and ensuring that the final product met the specified quality and performance requirements.
TEST METHODOLOGY
OVERVIEW (Mention the reason of adopting a particular test methodology for the project)
The iterative and modular testing methodology was adopted for CollegeHub to ensure continuous verification and validation throughout the development lifecycle. This approach allowed individual components to be developed and tested incrementally, facilitating early detection and correction of defects. By performing testing alongside development, the project achieved improved reliability, maintainability, and quality, while ensuring that the application met its functional and non-functional requirements before deployment.
TEST LEVELS (Define the Types of Testing to be executed on the Application Under Test (AUT))
The testing of CollegeHub was carried out at multiple levels to ensure the correctness and reliability of the application. Unit Testing was performed to validate individual modules and functions, while Integration Testing ensured proper interaction between the frontend, backend, and database components. System Testing was conducted to verify that the complete application met the specified functional and non-functional requirements. Additionally, User Interface Testing and Functional Testing were performed to ensure a responsive, user-friendly, and error-free experience across different browsers and operating systems.
BUG TRIAGE (Define resolution of each bug, prioritize bugs and determine a schedule for all “To Be Fixed Bugs’)
Bug triage for CollegeHub involved identifying, categorizing, and prioritizing defects based on their severity and impact on system functionality. Critical issues affecting core features such as user authentication, API communication, and database operations were assigned the highest priority and resolved immediately, while minor issues related to user interface and performance were scheduled for subsequent fixes. All identified bugs were tracked, analyzed, and resolved systematically to ensure the stability, reliability, and overall quality of the application before deployment.
TEST COMPLETENESS (Define the criteria that will deem your testing complete)
Testing for CollegeHub was considered complete when all planned functional and non-functional requirements had been verified and the corresponding test cases had been successfully executed. Completeness criteria included achieving full coverage of critical features such as user authentication, college browsing, course filtering, API communication, and database operations. All identified high-priority defects were resolved before deployment, while any minor issues were documented for future releases. The application was also validated for usability, responsiveness, and compatibility across supported browsers and operating systems to ensure a reliable and stable user experience.
TEST DELIVERABLES
(Mention all the Test Artifacts that will be delivered during different phases of the testing lifecycle)
• Test Plan • Test Cases • Requirement Traceability Matrix • Bug Reports • Test Strategy • Test Metrics
RESOURCE AND ENVIRONMENT NEEDS
TESTING TOOLS
Visual Studio Code Google Chrome Microsoft Edge Node.js Express.js PostgreSQL Postman (for API testing) Git and GitHub
TEST ENVIRONMENT (Minimum hardware requirements that will be used to test the Application)
Operating System: Windows (with compatibility verification for Linux and macOS) Runtime Environment: Node.js Backend Framework: Express.js Database Management System: PostgreSQL Frontend Technologies: HTML, CSS, JavaScript Web Browsers: Google Chrome and Microsoft Edge Development Environment: Visual Studio Code Network Environment: Localhost (development and testing environment)
ADDITIONAL COMMENTS
TEST PLAN
ITEMS TO TEST | TEST DESCRIPTION | TEST START DATE | TEST END DATE | RESPONSIBLE PERSON | STATUS | COMMENTS
User Registration | Verify successful account creation and input validation | 2026-06-01 | 2026-06-01 | Developer | PASSED | Working as expected
User Login Authentication | Validate login functionality and password verification | 2026-06-01 | 2026-06-02 | Developer | PASSED | bcrypt authentication implemented
College Data Retrieval | Verify fetching of college information from database | 2026-06-02 | 2026-06-02 | Developer | PASSED | API responses validated
College Browsing | Test display and navigation of college listings | 2026-06-02 | 2026-06-03 | Developer | PASSED | No issues observed
Course Filtering | Verify filtering colleges based on selected courses | 2026-06-03 | 2026-06-03 | Developer | PASSED | Accurate results obtained
Pagination | Validate page navigation and data loading | 2026-06-03 | 2026-06-04 | Developer | PASSED | Pagination functioning correctly
API Integration | Test communication between frontend and backend | 2026-06-04 | 2026-06-04 | Developer | PASSED | Endpoints responding correctly
Database Operations | Verify insertion and retrieval of records in PostgreSQL | 2026-06-04 | 2026-06-05 | Developer | PASSED | Queries executed successfully
User Interface Responsiveness | Test responsiveness across different screen sizes | 2026-06-05 | 2026-06-05 | Developer | PASSED | Responsive layout confirmed
Browser Compatibility | Validate application on Chrome and Edge browsers | 2026-06-05 | 2026-06-06 | Developer | PASSED | Compatible across tested browsers
Error Handling | Verify handling of invalid inputs and server errors | 2026-06-06 | 2026-06-06 | Developer | PASSED | Appropriate error messages displayed
Overall System Testing | Validate end-to-end functionality of CollegeHub | 2026-06-06 | 2026-06-07 | Developer | PASSED | System ready for deployment
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To determine scope, you must – > Precise customer requirement > Project Budget > Product Specification > Skills & talent of your test team
Note on C24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The objective of the testing is finding as many software defects as possible; ensure that the software under test is bug free before release. To define the test objectives, you should do 2 following steps: > List all the software features (functionality, performance, GUI…) which may need to test. > Define the target or the goal of the test based on above features
Note on C40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A Testing Type is a standard test procedure that gives an expected test outcome. all Testing Types are aimed at achieving one common goal “Early detection of all the defects before releasing the product to the customer. There are tons of Testing Types for testing software product. Your team cannot have enough efforts to handle all kind of testing. As Test Manager, you must set priority of the Testing Types > Which Testing Types should be focused for web application testing? > Which Testing Types should be ignored for saving cost? The commonly used testing types are: 1. Unit Testing 2. API Testing 3. Integration Testing 4. System Testing 5. Install/Uninstall Testing 6. Agile Testing You need to decide based on your project scope, time and cost the testing type(s) required for your project
Note on C48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test Criteria is a standard or rule on which a test procedure or test judgment can be based. There’re 2 types of test criteria as following Suspension Criteria Specify the critical suspension criteria for a test. If the suspension criteria are met during testing, the active test cycle will be suspended until the criteria are resolved. Exit Criteria It specifies the criteria that denote a successful completion of a test phase. The exit criteria are the targeted results of the test and are necessary before proceeding to the next phase of development. Example: 95% of all critical test cases must pass.