## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME:
INTERN NAME:
PROJECT NAME:
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | DD-MMM-YYYY
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | CollegeHub |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID
PROJECT MANAGER | Mrs. Harshada Topale
PROJECT SPONSOR | Mr. Tushar Topale
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
1 | 2026-05-25 | College data was not displayed on the frontend due to JavaScript errors | Integration | Yes | Verify DOM elements and API responses before rendering | Corrected the JavaScript logic and validated element IDs | Developer | Solved | Data retrieval functionality restored successfully
2 | 2026-05-26 | Pagination feature failed to load subsequent pages correctly | Functional | Yes | Review page calculation and data slicing logic | Modified pagination functions and tested with multiple datasets | Developer | Solved | Pagination works as expected
3 | 2026-05-28 | Frontend and backend communication issues during API requests | Integration | Yes | Validate API endpoints and server responses | Updated endpoint URLs and tested using Postman | Developer | Solved | Stable communication established
4 | 2026-05-30 | User authentication failed due to password validation issues | Security | Yes | Implement secure password handling mechanisms | Integrated bcrypt for password hashing and verification | Developer | Solved | Authentication system functions correctly
5 | 2026-06-01 | Null reference errors caused unexpected application behavior | Code Quality | Yes | Perform validation before accessing DOM elements | Added null checks and improved error handling | Developer | Solved | Application stability improved
6 | 2026-06-03 | Responsive layout inconsistencies observed on different screen sizes | User Interface | No | Optimize CSS for multiple resolutions | Updated media queries and layout properties | Developer | Solved | Improved user experience across devices