## GPI - Project Charter
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | CollegeHub
PROJECT SPONSOR | Tushar Topale
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE | 2026-05-20
EXPECTED COMPLETION DATE | 2026-06-25
ESTIMATED COST | N.A.
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE (Objective of a project represents the output or what you want to accomplish by doing it.) | The objective of CollegeHub is to provide a centralized and user-friendly platform for students to explore IT and Management colleges across India, enabling easy access to accurate college and course information through a secure and responsive web application.
BUSINESS CASE (A business case provides justification for undertaking a project. It evaluates the benefit, cost and risk of alternative options and provides a rationale for the preferred solution. ) | The business case for CollegeHub is to provide a centralized and cost-effective solution for students seeking information about IT and Management colleges across India. By consolidating college details into a single platform, the project reduces the effort and time required for manual searches while improving accessibility and user experience. The selected web-based solution offers scalability, ease of maintenance, and efficient data management, making it a practical and beneficial approach compared to traditional methods of gathering college information.
GOALS/METRICS (The project goal refers to achieving a desired outcome (performance goal) at a specific end date (time goal) employing a specific amount of resources (resource goal).) | The goal of CollegeHub is to develop and deliver a secure, responsive, and user-friendly web application that enables students to efficiently access information about IT and Management colleges across India. The success of the project is measured by the accurate retrieval of college data, reliable user authentication, seamless user experience, and timely completion of development using the available resources and technology stack.
EXPECTED DELIVERABLES (Describe the quantifiable goods or services that must be provided upon the completion of a project.) | The expected deliverables of CollegeHub include a fully functional web application with a responsive user interface, secure user authentication system, RESTful API services, and a PostgreSQL database containing information on IT and Management colleges across India. Additional deliverables include the source code, database schema, technical documentation, test reports, and deployment-ready application files, ensuring that the system meets the specified functional and quality requirements.
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE (This is functions and information which should be taken into account(estimated) in the development at the first stage. Or the stage for the development perios.) | The scope of CollegeHub includes the development of core features such as user authentication, college browsing, course filtering, database management, API integration, and a responsive user interface for accessing information on IT and Management colleges across India.
OUTSIDE OF SCOPE (This is functions which are planned to be done, but they are not reqired on the first stages.) | Features such as AI-based recommendations, college comparison, scholarship information, student reviews, and mobile application support are outside the scope of the initial development phase and are planned for future enhancements.
PROJECT RESOURCES AND COSTS
PROJECT TEAM (Mention the number of resources, who will be working on the project.) | NA
SUPPORT RESOURCES (Mention all the other resources that will be needed for the completion of the project.) | NA
COST ALLOCATION (Mention the cost of all the resources on an hourly/monthly/yearly basis. This will help to stick on to the project budget.) | NA
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER (Mention the Project Owner) | Prajakta Pattanaik
KEY STAKEHOLDERS (Mention all the stake holders involved in the project.) | NA
END CUSTOMER (Mention the client name.) | Cloud Counselage Pvt. Ltd.
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS (Risk is any unexpected event that can affect your project — for better or for worse. Risk can affect anything: people, processes, technology, and resources.) | Potential risks in CollegeHub include database connection failures, server downtime, inaccurate or outdated college information, security vulnerabilities, and compatibility issues across different browsers and operating systems.
ASSUMPTIONS (An assumption is any project factor that is considered to be true, real, or certain without empirical proof or demonstration.) | It is assumed that users have internet access, the college data stored in the database is accurate and up-to-date, and the system will operate in a supported browser and runtime environment.
CONSTRAINTS (Project constraints are anything that restricts or dictates the actions of the project team.) | The development of CollegeHub is constrained by the availability and accuracy of college data, limited development resources and time, internet dependency, and compatibility requirements across different browsers and operating systems.
MILESTONES
MILESTONE 1- Requirement Gathering ("Mention Completion Date in MM-DD-YYYY format. Requirement gathering is marked as complete after submission of SRS document") | 05-20-2026
MILESTONE 2 - Planning ("Mention Completion Date in MM-DD-YYYY format. Planning phase is considered after a duly completed Work Breakdown Structure (WBS), Project Schedule and RAID logs") | 05-22-2026
MILESTONE 3 - Design ("Mention Completion Date in MM-DD-YYYY format. Design stage is considered complete after submission of Design Specifications and Wireframe files") | 05-26-2026
MILESTONE 4 - Development ("Mention Completion Date in MM-DD-YYYY format. Development stage is considered complete after submission of Design Specifications and Wireframe files") | 2026-01-06
MILESTONE 5 - Testing ("Mention Completion Date in MM-DD-YYYY format. Testing stage is considered complete after submission of Test Reports") | 06-14-2026
MILESTONE 6 - Deployment ("Mention Completion Date in MM-DD-YYYY format. Deployment stage is considered complete after sybmitting the ") | 06-20-2026
MILESTONE 7 - Closure ("Mention Completion Date in MM-DD-YYYY format. Project closure is considered complete after handover of leasson learnt log, project report and installation guide") | 06-25-2026